P2P WATCH TOGETHER

Product, Architecture & Engineering Master Plan

Planning Baseline v0.1

| Document purpose | Authoritative planning baseline before repository implementation begins |
| --- | --- |
| Primary use case | Two people in different locations watching synchronized video over the Internet |
| Secondary use case | Up to three participants after the two-person experience is stable |
| Primary clients | Desktop web browser and Android browser / PWA |
| Status | Planning - architecture and feasibility not yet approved for production implementation |

Core architecture rule

If both users already have the media, synchronize playback only. If the guest does not have it, progressively transfer supported media peer-to-peer while it is being watched.

# Document Control

| Field | Value |
| --- | --- |
| Document ID | WT-MASTER-PLAN-001 |
| Version | 0.1 |
| Status | Planning baseline |
| Owner | Project maintainer |
| Last updated | 20 September 2026 |
| Change control | Major architectural changes must be captured in an ADR and reflected in PROJECT_STATE.md |

## How to Use This Document

This document is intended to remain the master reference for the project across implementation phases, coding assistants, pull requests, testing sessions, and future design changes. It defines what the product is, what it is not, how the system is expected to work, and the conditions that must be met before each phase can be considered complete.

Use this document to prevent scope drift and accidental architecture changes.

Use PROJECT_STATE.md as the live operational handoff; this document changes only when the baseline design itself changes.

Use Architecture Decision Records (ADRs) for decisions that modify or supersede this plan.

Do not treat later AI-generated implementation reports as authoritative unless repository state and tests independently confirm them.

# Table of Contents

| Section | Title |
| --- | --- |
| 1 | Executive Summary |
| 2 | Problem Statement and Product Goals |
| 3 | Primary User Journeys |
| 4 | Requirements Baseline |
| 5 | System Architecture |
| 6 | Internet Connectivity Model |
| 7 | Media Modes and Decision Logic |
| 8 | Media Pipeline and Format Strategy |
| 9 | Buffering, Caching and Seeking |
| 10 | Playback Synchronization Design |
| 11 | Security and Privacy Baseline |
| 12 | Diagnostics and Observability |
| 13 | Recommended Technology Baseline |
| 14 | Repository and Documentation Structure |
| 15 | Development and Review Workflow |
| 16 | Phase Roadmap and Exit Gates |
| 17 | Detailed Phase 0 Feasibility Checklist |
| 18 | Test Strategy |
| 19 | Browser Compatibility Policy |
| 20 | Risk Register |
| 21 | Security Verification Checklist |
| 22 | MVP and v1.0 Definitions |
| 23 | Post-v1 Candidate Features |
| 24 | Repository Bootstrap - Immediate Next Steps |
| 25 | Project Governance Rules |
| 26 | Technical Reference Baseline |
| A | PROJECT_STATE.md Template |
| B | Phase Pull Request Review Checklist |
| C | Initial Acceptance Metrics to Tune |

# 1. Executive Summary

The project will deliver a private, web-first watch-together experience optimized for two people in different locations, with a later path to three participants. It deliberately avoids building a centralized streaming platform. Instead, it combines synchronized local playback with peer-to-peer progressive media transfer.

Product thesis The application should feel like a simple private watch room. The system should decide whether to synchronize existing local media or progressively deliver the host's media to the guest. Users should not need to understand the underlying transport mode.

| Area | Baseline decision |
| --- | --- |
| Primary experience | Two-person synchronized playback over the public Internet |
| Mode A | Both users already have the same media; transfer only control/chat state |
| Mode B | Only host has media; progressively transfer supported content while guest watches |
| Client strategy | Web application / PWA first, with Android Chrome as a first-class target |
| Connectivity | WebRTC peer-to-peer where possible; signaling + STUN; TURN fallback when required |
| Media baseline | MP4 container with H.264 video and AAC audio for first Progressive Mode |
| Storage | Browser-side cache using OPFS where supported; cache is disposable by design |
| Control model | Host-authoritative playback clock for initial versions |
| Backend boundary | No permanent media upload to the application backend |
| Delivery philosophy | Phase-gated development with mandatory technical feasibility spikes before full implementation |

# 2. Problem Statement and Product Goals

## 2.1 Problem Statement

Existing watch-together tools frequently impose one or more constraints that do not fit this use case: payment requirements, meeting-duration limits, small upload limits, reduced video quality, centralized hosting, or lack of reliable synchronization for large local files. The target use case is different: two people may already have the same video, or only one participant may have a large personal/local video that should be watched together without first uploading it to a cloud video platform.

## 2.2 Product Goals

Provide synchronized playback for two people in different states/countries over ordinary Internet connections.

Support both local-file synchronization and progressive peer-to-peer receiving/watching.

Preserve original quality when the connection is fast enough; do not impose an arbitrary 800 MB or 1 GB product limit.

Allow play, pause, and seek actions to remain synchronized across participants.

Provide lightweight text chat, reactions, room presence, and clear buffering/connection status.

Continue playback from already buffered data during short network interruptions where feasible.

Avoid permanent server-side media storage and unnecessary account requirements.

Create a maintainable project with explicit documentation, phase gates, security controls, and reproducible tests.

## 2.3 Non-Goals for MVP

Building a public video-sharing or content-hosting platform.

Circumventing DRM or retransmitting protected commercial streaming services.

Supporting every container, codec, subtitle, and audio format in the first release.

Large group watch parties or webinar-scale rooms.

Permanent cloud storage, media libraries, creator channels, or public discovery.

Native iOS/Android applications before the web architecture is proven.

Voice/video calls in the MVP; they may be added after core playback is stable.

# 3. Primary User Journeys

## 3.1 Journey A - Both Participants Have the Same Video

1. Host creates a private room and shares the invite.

2. Guest joins.

3. Both select their local copy of the video.

4. The application compares metadata/fingerprints to determine compatibility.

5. Both become Ready.

6. Playback starts from a shared authoritative timeline.

7. Play, pause, seek, chat, and reactions remain synchronized.

## 3.2 Journey B - Only the Host Has the Video

1. Host creates a private room and selects a supported local video.

2. Guest joins and does not have a matching local copy.

3. The application negotiates a peer-to-peer media path.

4. The host media is segmented/chunked and transferred progressively.

5. The guest caches incoming media and builds an initial buffer.

6. Playback begins before the complete file has arrived.

7. Transfer continues ahead of playback and prioritizes the current seek area.

8. If the connection drops briefly, already-buffered content continues until the buffer is exhausted.

9. When the connection returns, missing data resumes and playback state re-synchronizes.

Important distinction Mode B is not screen sharing and is not a centralized streaming service. It is a private progressive media-transfer experience between authorized participants, with local playback on the receiving device.

# 4. Requirements Baseline

## 4.1 Functional Requirements

| ID | Capability | Requirement |
| --- | --- | --- |
| FR-001 | Room creation | A user can create a private watch room and obtain a secure invite. |
| FR-002 | Room join | A guest can join from a supported browser using the invite. |
| FR-003 | Presence | Participants can see connection and readiness state. |
| FR-004 | Local media selection | Participants can select a local media file without uploading it to the signaling backend. |
| FR-005 | Media comparison | The application can determine whether local files are likely identical/compatible. |
| FR-006 | Play sync | A host play action propagates to the guest timeline. |
| FR-007 | Pause sync | A host pause action propagates to the guest timeline. |
| FR-008 | Seek sync | A seek changes the authoritative playback position and moves peers accordingly. |
| FR-009 | Drift correction | The system detects and corrects unacceptable playback drift. |
| FR-010 | Progressive transfer | A guest can begin playback before a supported host file is fully transferred. |
| FR-011 | Buffer management | The receiver maintains and reports a forward playback buffer. |
| FR-012 | Seek prioritization | After seeking, transfer prioritizes media near the new playback location. |
| FR-013 | Resume | Interrupted transfer can resume without restarting the entire media transfer. |
| FR-014 | Chat | Participants can exchange short text messages. |
| FR-015 | Reactions | Participants can send lightweight reactions. |
| FR-016 | Reconnect | A participant can recover from a temporary network interruption. |
| FR-017 | Cache controls | A user can inspect and clear application media cache. |
| FR-018 | Diagnostics | Development builds expose connection path, RTT, drift, buffer, and transfer metrics. |

## 4.2 Non-Functional Requirements

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-001 | Privacy | No permanent application-server media storage by default. |
| NFR-002 | Security | Production traffic uses HTTPS/WSS and encrypted WebRTC transport. |
| NFR-003 | Scalability | MVP optimized for two peers; architecture should not prevent later three-peer rooms. |
| NFR-004 | Resilience | Short network interruptions should not corrupt state or require a full transfer restart. |
| NFR-005 | Compatibility | Chrome desktop and Chrome Android are first-class test targets. |
| NFR-006 | Quality | Media should be preserved without re-encoding when the file is already compatible and bandwidth permits. |
| NFR-007 | Observability | Failures must be diagnosable using structured client/server logs and WebRTC metrics. |
| NFR-008 | Maintainability | Protocol, sync engine, transfer engine, and signaling layers remain modular. |
| NFR-009 | Safety | Untrusted messages, filenames, sizes, and peer-provided metadata are validated before use. |
| NFR-010 | Cost control | TURN relay usage must be visible because relaying multi-GB media can create significant bandwidth cost. |

# 5. System Architecture

## 5.1 High-Level Architecture

+---------------------+
                         |  Signaling Service  |
                         | room + SDP/ICE only |
                         +----------+----------+
                                    |
                          connection negotiation
                                    |
        +---------------------------+---------------------------+
        |                                                       |
+-------v--------+                                      +-------v--------+
| Host Browser   |<========= WebRTC / P2P ============>| Guest Browser  |
| player         |   control + chat + media chunks     | player         |
| sync engine    |                                      | sync engine    |
| transfer engine|                                      | receiver/cache |
+----------------+                                      +----------------+
        \__________________ STUN / TURN as needed __________________/

The signaling service coordinates room membership and WebRTC negotiation. It should not become the default media path. ICE attempts a direct peer-to-peer route; TURN exists as a reliability fallback when a direct path cannot be established.

## 5.2 Component Boundaries

| Component | Responsibilities | Must not own |
| --- | --- | --- |
| Web UI | Room UX, media selection, player controls, chat/reactions, diagnostics presentation | Protocol rules scattered through components |
| Protocol package | Typed message schemas, validation, versioning, serialization | Player UI state |
| Sync engine | Authoritative timeline, clock offset estimation, drift policy, action ordering | Media segmentation or WebRTC signaling |
| Transfer engine | Chunk scheduling, backpressure, acknowledgements, retransmission, seek priority | Playback authority |
| Media pipeline | Compatibility checks, segmentation, MSE append path, source metadata | Room authentication |
| Cache layer | OPFS storage, segment index, space estimation, cleanup | Authoritative room state |
| Signaling service | Room creation/join, transient signaling messages, abuse/rate limits | Permanent media or chat history |
| Diagnostics | Metrics collection, WebRTC stats normalization, exportable debug snapshot | Secret tokens or raw media |

# 6. Internet Connectivity Model

## 6.1 Signaling

Browsers on different networks cannot reliably discover and negotiate direct connectivity without an exchange channel. The signaling service will provide a temporary WebSocket-based path for offers, answers, ICE candidates, room lifecycle state, and selected diagnostics. Signaling data should expire quickly and should not include media bytes.

## 6.2 ICE, STUN and TURN

| Path | Meaning | Product impact |
| --- | --- | --- |
| Direct P2P | Peers establish a direct route using ICE/STUN. | Preferred. Large media goes directly between participants. |
| TURN relay | Direct route fails; encrypted WebRTC traffic is relayed. | Reliable but can be costly for multi-GB media. Must be measured and surfaced. |
| Signaling only | Backend carries negotiation messages only. | Low bandwidth and inexpensive relative to media transfer. |

Cost guardrail Before calling Progressive Mode production-ready, test how often representative Wi-Fi and mobile networks require TURN and estimate worst-case relay traffic. Do not assume all users will connect directly.

# 7. Media Modes and Decision Logic

## 7.1 Mode Selection

Host selects media
        |
        v
Guest has compatible fingerprint?
     /        \
   YES        NO
    |          |
Local Sync   Progressive Watch
    |          |
No media     Buffer -> play -> continue receiving
transfer

## 7.2 Mode A - Local Sync

Mode A should be extremely lightweight. Both devices play their own local file. Network traffic consists primarily of room state, playback events, synchronization heartbeats, chat, reactions, and diagnostics. File size is therefore largely irrelevant once compatibility has been confirmed.

## 7.3 Mode B - Progressive Watch

Mode B turns the host into the source for a private progressive media session. The receiver stores incoming segments locally and feeds playable media to the browser. Playback begins only after the required initialization data and a minimum safe buffer are available.

Transfer speed higher than media bitrate: buffer grows and may eventually contain the remainder of the video.

Transfer speed approximately equal to media bitrate: maintain a conservative safety buffer and warn if it shrinks.

Transfer speed below media bitrate: initial buffering grows, playback may need coordinated pauses, or a future quality-reduction path may be required.

# 8. Media Pipeline and Format Strategy

## 8.1 Initial Compatibility Contract

MVP Progressive Mode media contract Container: MP4. Video: H.264/AVC. Audio: AAC. Local Sync may support additional files whenever the browser itself can play them.

## 8.2 Progressive Playback Pipeline

Host File
   |
   v
Compatibility inspection
   |
   v
MP4 parsing / fragmentation
   |
   v
Media segments
   |
   v
Transport chunks over WebRTC
   |
   v
Receiver reassembly -> integrity/order checks -> OPFS cache
   |
   v
MSE SourceBuffer -> HTML5 video element

## 8.3 Why Segments and Transport Chunks Are Separate

A media segment is a playback-level unit understood by the media pipeline. A transport chunk is a smaller network message used to move a segment safely through RTCDataChannel without relying on large single-message behavior. This separation allows transport tuning without redefining the media timeline.

## 8.4 Sender Backpressure

The sender must monitor RTCDataChannel buffering and pause/resume writes using bufferedAmount and bufferedAmountLowThreshold (or equivalent logic). Unbounded writes can exhaust memory or produce unstable behavior. Chunk size and watermarks must be benchmarked on desktop Chrome and Android Chrome during Phase 5.

# 9. Buffering, Caching and Seeking

## 9.1 Buffer Model

| State | Example meaning | Action |
| --- | --- | --- |
| Healthy | Playback at 20:00; buffer available to 38:00 | Continue normal ahead-of-playback transfer |
| Low | Playback at 20:00; buffer available to 21:00 | Raise priority of near-future media and show warning |
| Critical | Playback is about to consume final buffered segment | Coordinate pause if required; avoid letting peers silently diverge |
| Recovered | Throughput improves and safety margin is restored | Resume ordinary background fetching |

## 9.2 Seek Priority

Seeking must cancel or demote obsolete near-term transfer work and prioritize segments surrounding the new authoritative position. The guest should not be forced to receive every earlier byte before playback can resume at the new location.

Before seek:  request 35:00 -> 35:05 -> 35:10 -> ...
Host seeks:   01:22:15
After seek:   request init (if needed) -> 01:22:00 -> 01:22:05 -> 01:22:10 -> ...
Then resume lower-priority background filling.

## 9.3 Browser Cache

Large received media should use browser file/storage primitives such as the Origin Private File System (OPFS) where supported. The application must estimate available storage before accepting large transfers, maintain an index of cached media/segments, and provide explicit cleanup controls.

Do not use localStorage for media bytes.

Treat cache as disposable unless persistent storage is successfully granted.

Handle eviction or low-storage errors without corrupting room state.

Never trust the sender-provided filename as a safe local path.

# 10. Playback Synchronization Design

## 10.1 Host-Authoritative Timeline

The host maintains the canonical playback state for the initial product. Events carry an ordered sequence number, playback position, and sender timestamp. Guests estimate the expected host position at message receipt and adjust their player accordingly.

## 10.2 Drift Policy - Initial Target

| Observed drift | Initial policy | Notes |
| --- | --- | --- |
| < 250 ms | Ignore | Avoid visible micro-corrections. |
| 250-1000 ms | Gentle rate correction | Temporarily adjust playback rate within a narrow safe range. |
| > 1000 ms | Hard seek/resync | Use authoritative expected position. |
| Repeated instability | Pause/rebuffer or show degraded-state UI | Investigate network and media-buffer health. |

Threshold status These values are starting hypotheses, not final constants. Phase 3 real-device tests must determine acceptable thresholds and correction behavior.

## 10.3 Example Control Message

{
  "protocolVersion": 1,
  "type": "PLAY",
  "sequence": 184,
  "positionMs": 3821421,
  "sentAtMs": 1789916245123
}

## 10.4 Protocol Message Families

| Family | Examples |
| --- | --- |
| Room | ROOM_JOIN, ROOM_LEAVE, READY, NOT_READY, ROLE_CHANGE |
| Media | MEDIA_INFO, MEDIA_MATCH, MEDIA_UNSUPPORTED |
| Playback | PLAY, PAUSE, SEEK, SYNC_HEARTBEAT |
| Transfer | TRANSFER_MANIFEST, SEGMENT_REQUEST, CHUNK, ACK, RETRY, CANCEL |
| Buffer | BUFFER_STATUS, CACHE_STATUS, LOW_BUFFER |
| Social | CHAT, REACTION |
| Connection | PING, PONG, RECONNECT_STATE, ERROR |

# 11. Security and Privacy Baseline

## 11.1 Security Principles

Assume all peer-provided messages and media metadata are untrusted.

Validate protocol schemas and maximum sizes before allocation or processing.

Use HTTPS/WSS in production and encrypted WebRTC transport.

Use high-entropy room/invite secrets; do not rely on a short human-readable code as the only secret.

Expire rooms and signaling state automatically.

Rate-limit room creation, join attempts, signaling message volume, and obvious abuse patterns.

Enforce maximum participant count and per-channel message size.

Apply Content Security Policy and safe rendering practices for chat/user-controlled text.

Use short-lived TURN credentials rather than hard-coded static secrets.

Keep diagnostics free of sensitive room secrets and raw media.

## 11.2 Privacy Model

| Data | Default handling |
| --- | --- |
| Media | Peer-to-peer where possible; no permanent storage on signaling backend |
| Chat/reactions | Ephemeral room state unless a future feature explicitly persists it |
| Room state | Temporary and automatically expired |
| Accounts | Not required for MVP |
| Analytics | Not required for MVP |
| Peer IP/network metadata | May be exposed as part of direct WebRTC connectivity; document accurately |
| TURN relay | Relay sees traffic flow metadata; content remains protected by WebRTC encryption |

# 12. Diagnostics and Observability

A watch-together product fails in subtle ways: direct versus relayed paths, clock drift, low forward buffer, poor sender upload, browser throttling, mobile background behavior, and storage pressure can all look like generic "video lag" unless measured.

| Metric | Purpose |
| --- | --- |
| ICE candidate/path type | Identify direct P2P versus TURN relay |
| RTT / jitter | Explain control latency and instability |
| Transfer throughput | Compare delivery speed to encoded media bitrate |
| Buffered duration | Predict whether playback can survive a temporary slowdown |
| Playback drift | Evaluate sync quality and correction thresholds |
| RTCDataChannel bufferedAmount | Detect sender backpressure |
| Cache bytes / storage estimate | Prevent storage exhaustion |
| Reconnect count / duration | Measure session resilience |
| Codec/container capability | Explain Progressive Mode availability |

Example developer diagnostics
Connection path : Direct P2P
RTT             : 62 ms
Media bitrate   : 5.1 Mbps
Transfer        : 18.4 Mbps
Forward buffer  : 18m 42s
Playback drift  : 84 ms
Cache used      : 1.27 GB
ICE state       : connected

# 13. Recommended Technology Baseline

| Layer | Initial choice | Reason |
| --- | --- | --- |
| Web client | TypeScript + React + Vite + PWA | Fast development, strong ecosystem, installable web experience |
| Playback | HTML5 video + Media Source Extensions | Native browser playback with programmatic append path |
| P2P | WebRTC PeerConnection + RTCDataChannel | Browser-supported encrypted peer connectivity and binary data |
| Media parsing | MP4Box.js feasibility investigation | MP4 parsing/fragmentation without immediately requiring a server transcode stack |
| Browser storage | OPFS where available | Suitable for larger origin-private binary cache |
| Signaling | Node.js + TypeScript + WebSocket | Simple transient signaling with shared types |
| Unit tests | Vitest | TypeScript-friendly test runner |
| Browser tests | Playwright | Multi-context end-to-end automation |
| Quality | ESLint + Prettier + strict TypeScript | Consistency and defect prevention |
| CI security | Gitleaks, CodeQL, dependency review/updates | Early secrets/static/dependency checks |

# 14. Repository and Documentation Structure

project/
|-- apps/
|   `-- web/
|-- services/
|   `-- signaling/
|-- packages/
|   |-- protocol/
|   |-- sync-engine/
|   `-- transfer-engine/
|-- docs/
|   |-- PROJECT_CHARTER.md
|   |-- ARCHITECTURE.md
|   |-- PROTOCOL.md
|   |-- MEDIA_PIPELINE.md
|   |-- SECURITY.md
|   |-- TEST_PLAN.md
|   |-- COMPATIBILITY.md
|   |-- ROADMAP.md
|   `-- adr/
|-- PROJECT_STATE.md
|-- README.md
|-- CONTRIBUTING.md
|-- LICENSE
`-- .gitignore

## 14.1 PROJECT_STATE.md Contract

Current version and phase

Current branch / active pull request

Completed work

Current accepted architecture

Known failures and blockers

Tests completed

Manual tests still required

Next exact step

Decisions that must not be silently reverted

Links to relevant ADRs and issue/PR numbers

## 14.2 Initial ADR Set

| ADR | Decision |
| --- | --- |
| ADR-0001 | Web-first / PWA product strategy |
| ADR-0002 | WebRTC peer-to-peer transport with signaling + STUN + TURN fallback |
| ADR-0003 | Host-authoritative playback synchronization |
| ADR-0004 | Two media modes: Local Sync and Progressive Watch |
| ADR-0005 | Initial Progressive Mode media contract: MP4/H.264/AAC |
| ADR-0006 | No permanent backend media storage |
| ADR-0007 | OPFS-based cache investigation for large received media |
| ADR-0008 | Two-person reliability before three-person rooms |

# 15. Development and Review Workflow

main
  |
  +-- phase/0-feasibility
  +-- phase/1-foundation
  +-- phase/2-p2p
  +-- phase/3-sync
  +-- phase/4-room-ux
  +-- phase/5-progressive-spike
  ...

1. Create a phase/feature branch.

2. Implement only the current approved scope.

3. Run unit/integration/browser tests.

4. Open a pull request.

5. Independently inspect the actual PR head and diff; do not rely only on an implementation assistant summary.

6. Fix findings and re-run relevant tests.

7. Merge after the phase exit gate is met.

8. Update PROJECT_STATE.md and any affected ADRs.

9. Tag meaningful milestones when appropriate.

Review rule The repository state, pull request diff, tests, and real-device evidence are authoritative. Assistant-generated reports are supporting material only.

# 16. Phase Roadmap and Exit Gates

| Phase | Name | Scope | Exit gate |
| --- | --- | --- | --- |
| Phase 0 | Architecture & Feasibility | Technical spikes only: WebRTC across networks, binary DataChannel, large local file access, OPFS, MP4 fragmentation, MSE append playback, Android Chrome participation. | Proceed only if the complete Progressive Mode concept appears feasible on target browsers. |
| Phase 1 | Application Foundation | Monorepo, TypeScript/React/PWA shell, local player, file picker, media metadata, capability detection, test baseline. | Supported local MP4 plays reliably on desktop Chrome and Android Chrome. |
| Phase 2 | Internet P2P Foundation | Signaling, room create/join, WebRTC negotiation, STUN, DataChannel, disconnect/reconnect, network diagnostics. | Desktop and Android on different networks exchange messages reliably and path type is observable. |
| Phase 3 | Local Sync Mode | Host clock, play/pause/seek, heartbeat, drift detection/correction, readiness, media fingerprinting. | A 60+ minute video remains acceptably synchronized during real-device testing. |
| Phase 4 | Room Reliability & UX | Secure invite, participant state, reconnect UX, chat, reactions, errors, security validation, diagnostics panel. | Two-person Local Sync is usable as a real product rather than a lab demo. |
| Phase 5 | Progressive Watch Technical Spike | MP4 parsing/fragmentation, MSE, binary transfer, transport chunking, backpressure, OPFS, seek behavior. | Guest begins watching before complete transfer and continues while additional media arrives. |
| Phase 6 | Progressive Watch Productionization | Resume, adaptive buffer, seek priority, missing-chunk recovery, integrity checks, transfer progress, low storage, network recovery. | Multi-GB supported media completes end-to-end over the Internet without requiring full pre-download. |
| Phase 7 | Cross-Browser Hardening | Chrome/Edge/Firefox/Safari where available; compatibility matrix; graceful feature fallbacks. | Support matrix is backed by actual tests, not assumptions. |
| Phase 8 | Three-Person Rooms | Third participant, multi-peer state distribution, transfer topology/bandwidth behavior, participant-specific buffering. | Three users work without regressing the established two-user experience. |
| Phase 9 | v1.0 Hardening | Security review, CodeQL/Gitleaks/dependency checks, large-file/network-loss/latency/storage tests, documentation finalization. | All blocker/high-severity issues closed or explicitly accepted; v1.0 release criteria met. |

# 17. Detailed Phase 0 Feasibility Checklist

Phase 0 exists to retire the highest architectural risks before a polished application is built. Each spike should be intentionally small, independently reproducible, and documented with observed browser/device behavior.

| ID | Spike | Test | Evidence |
| --- | --- | --- | --- |
| F0-01 | Large local file access | Select a multi-GB file in desktop Chrome and Android Chrome; inspect metadata without reading the entire file into memory. | Pass/Fail + memory notes |
| F0-02 | Internet WebRTC | Establish a PeerConnection between devices on different networks and exchange structured messages. | Direct/relay path recorded |
| F0-03 | Binary DataChannel | Transfer binary chunks with backpressure and verify byte integrity. | Throughput + safe chunk range |
| F0-04 | OPFS cache | Write/read large sequential chunks; inspect quota and cleanup behavior. | Storage behavior documented |
| F0-05 | MSE baseline | Append fragmented MP4 data and play it using Media Source Extensions. | Playable on target browsers |
| F0-06 | Progressive assembly | Start playback before all segments are available, then append more while playing. | Continuous playback demonstrated |
| F0-07 | Seek experiment | Jump to a not-yet-buffered position and prioritize receiving the relevant segment range. | Recovery behavior documented |
| F0-08 | Android behavior | Repeat critical spikes on real Android Chrome, including screen lock/background observations. | Target-device evidence captured |

# 18. Test Strategy

## 18.1 Test Layers

| Layer | Examples | When required |
| --- | --- | --- |
| Unit | Clock math, drift policy, validators, segment scheduler, cache index | Every PR affecting core logic |
| Component | Player controller, room state machine, transfer queue | Feature PRs |
| Browser E2E | Create/join, ready, play, pause, seek, reconnect | From Phase 2 onward |
| Network integration | Different networks, direct/relay path, constrained bandwidth | Phase gates |
| Real device | Mac/desktop browser <-> Android Chrome | Every relevant phase exit gate |
| Security | Malformed messages, oversized chunks, invite abuse, CSP, secrets checks | From first networked phase onward |
| Regression | Previously passed critical user journeys | Before merge/release |

## 18.2 Network Matrix

| Host | Guest | Expected test |
| --- | --- | --- |
| Wi-Fi | Wi-Fi | Baseline broadband P2P |
| Wi-Fi | 5G | Common desktop-to-mobile case |
| 5G | Wi-Fi | Mobile source behavior |
| 5G | 5G | NAT/reliability stress case |
| Constrained Wi-Fi | Wi-Fi | Buffer depletion/recovery |
| Wi-Fi | High-latency profile | Sync/control resilience |
| Wi-Fi with interruption | Wi-Fi | Reconnect + cached playback continuity |

## 18.3 Media Test Matrix

| Case | Purpose |
| --- | --- |
| 100-300 MB short MP4 | Fast functional regression |
| 1-3 GB H.264/AAC MP4 | Primary real-world target |
| Long 60-120 minute video | Drift and cache durability |
| Higher bitrate 1080p | Throughput and buffer stress |
| Unsupported container/codec | Graceful capability error |
| File near available storage limit | Low-storage handling |
| Seek far ahead | Priority scheduling |
| Temporary transfer interruption | Resume and buffer continuity |

# 19. Browser Compatibility Policy

Browser support will be evidence-based. A browser is not marked supported because individual APIs appear in documentation; the full user journey must pass on the actual browser/device combination.

| Platform | Local Sync target | Progressive target | Initial status |
| --- | --- | --- | --- |
| Chrome macOS | Yes | Yes | Required |
| Chrome Windows | Yes | Yes | Required/secondary desktop |
| Chrome Android | Yes | Yes | Required |
| Edge desktop | Yes | Yes | Expected after Chrome baseline |
| Firefox desktop | Yes | Evaluate | Phase 7 |
| Firefox Android | Evaluate | Evaluate | Phase 7 |
| Safari macOS | Evaluate | Evaluate | Phase 7 |
| Safari/iOS | Evaluate | Evaluate | Later real-device gate |

# 20. Risk Register

| Risk | Severity | Description | Mitigation |
| --- | --- | --- | --- |
| R-001 | High | TURN relay cost for multi-GB sessions | Instrument direct/relay path; test representative networks; define relay policy/cost limits. |
| R-002 | High | Browser media compatibility differs by codec/container | Narrow MVP media contract; feature-detect; fail cleanly; expand only with tests. |
| R-003 | High | Progressive MP4/MSE design fails on Android target | Mandatory Phase 0 spike before application build. |
| R-004 | High | WebRTC DataChannel stalls/memory pressure under large transfers | Chunking + bufferedAmount backpressure + benchmarked thresholds. |
| R-005 | Medium | Browser storage quota/eviction disrupts cache | Estimate quota, handle errors, explicit cleanup, avoid assuming persistence. |
| R-006 | Medium | Host upload lower than media bitrate | Adaptive buffer; coordinated pause; later optional quality conversion. |
| R-007 | Medium | Mobile background/lock throttles browser | Real Android lifecycle tests; document limitations; consider native app only if necessary. |
| R-008 | Medium | Participants have different cuts/encodes in Local Sync | Fingerprint/metadata checks; warn/fallback to host transfer. |
| R-009 | Medium | Clock/drift correction causes visible jumps | Real-device tuning; separate small/medium/large drift policies. |
| R-010 | Low/Medium | Scope creep into streaming platform/social product | Maintain non-goals and phase gates; ADR required for major expansion. |

# 21. Security Verification Checklist

| ID | Control |
| --- | --- |
| SEC-01 | Room invite entropy and expiration |
| SEC-02 | Join/create rate limits |
| SEC-03 | Schema validation for every message family |
| SEC-04 | Maximum binary chunk/message size |
| SEC-05 | Backpressure and memory exhaustion tests |
| SEC-06 | Safe handling of media metadata and filenames |
| SEC-07 | Chat output escaping / CSP |
| SEC-08 | Short-lived TURN credentials |
| SEC-09 | No secrets in repository or client bundle |
| SEC-10 | Dependency and static security scans |
| SEC-11 | No media persisted in signaling service |
| SEC-12 | Privacy review of diagnostics/logging |

# 22. MVP and v1.0 Definitions

## 22.1 MVP Definition

Two users on different networks can create/join a private room.

Local Sync works with matching local files.

Supported Progressive Mode media begins playing before the full file transfers.

Play, pause, and seek remain synchronized.

The receiver buffers and continues receiving ahead of playback.

Temporary network interruption can reconnect without starting the session from zero.

Chat and reactions work.

The application reports meaningful connection/buffer state.

No permanent server-side media storage is required.

## 22.2 v1.0 Release Gate

| Area | Required evidence |
| --- | --- |
| Core UX | Complete two-person user journeys pass on required target clients |
| Progressive media | Multi-GB supported file completes end-to-end while being watched |
| Synchronization | Long-session drift remains within agreed acceptance criteria |
| Resilience | Reconnect, seek, and low-buffer behaviors are validated |
| Security | Threat review + CI security checks + malformed protocol tests |
| Compatibility | Published support matrix reflects real tests |
| Documentation | README, architecture, protocol, security, test plan, PROJECT_STATE updated |
| Known issues | No unresolved blocker/high issue unless explicitly accepted and documented |

# 23. Post-v1 Candidate Features

The following are explicitly deferred until the two-person web experience is stable:

Voice chat

Subtitle synchronization and shared subtitle selection

Multiple audio tracks

Playlists

AV1 and additional codec support

HEVC where reliably supported

Automatic remuxing

Optional transcoding / quality variants

Native Android application

Native iOS application

Desktop application

Privacy relay mode

Watch history

Larger group rooms

# 24. Repository Bootstrap - Immediate Next Steps

| Step | Action | Notes |
| --- | --- | --- |
| 1 | Choose final product/repository name | Do not block architecture on branding; a working name is acceptable. |
| 2 | Create GitHub repository | Start with no application feature code. |
| 3 | Commit documentation baseline | README, project charter, architecture, roadmap, security, test plan, compatibility, ADR directory, PROJECT_STATE. |
| 4 | Add branch/review protections | Protect main once initial bootstrap is stable. |
| 5 | Create Phase 0 branch | phase/0-feasibility or equivalent. |
| 6 | Run Phase 0 spikes | Record evidence, browser versions, devices, network path, failures. |
| 7 | Independent Phase 0 review | Verify actual code/results and decide whether architecture is approved. |
| 8 | Authorize Phase 1 only after gate passes | If a feasibility spike fails, revise architecture via ADR before proceeding. |

# 25. Project Governance Rules

1. Do not implement out-of-phase features because they are convenient or interesting.

2. Do not silently replace an accepted architectural decision; create or supersede an ADR.

3. Update PROJECT_STATE.md after every significant milestone or verified test gate.

4. Never substitute emulator/simulator evidence for an explicitly required real-device gate.

5. Keep playback synchronization independent from media transfer.

6. Keep signaling independent from media transport.

7. Do not introduce server-side media storage as a shortcut without an explicit architecture decision.

8. Optimize the two-person experience before adding a third participant.

9. Progressive Mode is capability-detected; unsupported media must fail clearly and safely.

10. Security validation begins with the protocol design rather than being deferred to release hardening.

11. Every phase has an explicit exit gate, and blocker-level failures prevent progression.

12. Documentation and testing are deliverables, not cleanup tasks.

13. Actual repository state and test evidence override summaries produced by tools or assistants.

# 26. Technical Reference Baseline

These references are starting points for implementation research. Exact browser behavior must still be verified against the target versions and real devices during the applicable phase.

WebRTC API: Open reference

RTCDataChannel: Open reference

RTCDataChannel.send(): Open reference

RTCPeerConnection: Open reference

Media Source Extensions: Open reference

MediaSource: Open reference

Origin Private File System: Open reference

Storage quotas and eviction: Open reference

MP4Box.js: Open reference

# Appendix A - PROJECT_STATE.md Template

# PROJECT_STATE

## Project
- Name: TBD
- Current version: 0.0.x
- Current phase: Phase 0 - Feasibility
- Active branch: phase/0-feasibility
- Active PR: none

## Accepted Architecture
- Web-first / PWA
- Two-person first
- WebRTC P2P
- Signaling + STUN + TURN fallback
- Mode A: Local Sync
- Mode B: Progressive Watch
- MP4/H.264/AAC Progressive baseline

## Completed
- ...

## Tests Completed
- ...

## Manual Tests Required
- ...

## Known Issues / Blockers
- ...

## Decisions Not To Revert
- ...

## Next Exact Step
1. ...

## Relevant ADRs / PRs
- ...

# Appendix B - Phase Pull Request Review Checklist

[ ] Scope matches current phase and approved ADRs.

[ ] Actual PR head and diff independently reviewed.

[ ] No unrelated architectural refactor hidden in feature work.

[ ] Tests added/updated for changed behavior.

[ ] Automated tests pass in CI.

[ ] Required real-device/manual evidence is attached or recorded.

[ ] Protocol/message changes are versioned/documented.

[ ] Security validation covers new external inputs.

[ ] No secrets or generated large media accidentally committed.

[ ] PROJECT_STATE.md updated.

[ ] Affected ADR/docs updated.

[ ] Phase exit gate explicitly assessed before merge.

# Appendix C - Initial Acceptance Metrics to Tune

| Metric | Starting hypothesis | Finalization phase |
| --- | --- | --- |
| Local sync drift | Usually < 250 ms visible difference | Phase 3 |
| Hard resync threshold | Around > 1000 ms | Phase 3 |
| Initial Progressive buffer | 30-60 seconds or adaptive equivalent | Phase 5/6 |
| Transport chunk size | Benchmark; do not hard-code from assumption | Phase 0/5 |
| Forward buffer low threshold | Derived from bitrate + observed throughput | Phase 6 |
| Reconnect target | Recover without full room recreation when feasible | Phase 2/4/6 |
| Supported file size | No arbitrary product cap; bounded by browser/storage/network feasibility | Phase 6/7 |

Baseline approval point The project should begin implementation with Phase 0 only. Full application development is authorized after the feasibility results confirm or appropriately revise the architecture defined in this document.